## Gantt Chart Template
Egypt Nexus | Start date | End date | Assigned | Status | Duration
Egypt nexus project | 2025-08-23 | 2025-11-15 | Pixora | In process | 84
Research & Moodboard | 2025-08-23 | 2025-09-06 | All | In process | 14
Logo & Visual Identity | 2025-09-06 | 2025-09-20 | All | In process | 14
Posters & Social Media | 2025-09-20 | 2025-10-11 | All | In process | 21
UI/UX - Website 4.1 | 2025-10-11 | 2025-10-25 | Tarneem,Menna,Omar Magdy | In process | 14
App 4.2 | 2025-10-11 | 2025-10-25 | Yusuf, Hossam, Omar khalid | In process | 14
Collateral | 2025-10-25 | 2025-11-01 | All | In process | 7
Integration | 2025-11-01 | 2025-11-08 | All | In process | 7
Prototype | 2025-11-08 | 2025-11-13 | All | In process | 5
Final Presentation | 2025-11-13 | 2025-11-15 | All | In process | 2

## Assignees and Status
Assignees
Tarneem
Omar Magdy
Omar Khalid
Hossam
Menna
Yusuf